REGULATORY AND TECHNICAL TRAINING WORK PLAN

2022/2023 FISCAL YEAR

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Trade Name** | **Task** | **Date Required** | **# IWG Members** | **Status** |
| Carpenter | Translation Workshop | Names due January 20, 2023  Work: Mar 13-16/23 in OTT | 1 Red Seal  ER/EE REP  Bilingual | Names Needed |
| Construction Craft Worker | Red Seal Occupational Standards (RSOS) Development | August 1, 2023 apps due  Names due Sept 16, 2023  Work: Nov 6-24/23 | TBD | TBD |
| Crane – Mobile Crane Operator | * Red Seal Examination Development – MB lead | July 29, 2022 apps due  Work:   * Part 1:Now-March 20, 23   2 yr commitment   * Part 2: April –May 2023 | * 3 Red Seal   ER/EE REP   * 4 Red Seal   ER/EE REP  Different members | Names Needed |
| * Translation Workshop | August 12, 2022 app due  Name to ESDC is Sept 2  Work: Dec 13-15 in Ottawa | 1 Red Seal  Bilingual  Development workshop held in Ottawa. | Complete |
| Crane – Tower Crane Operator | Red Seal Occupational Standards (RSOS) Development | July 29, 2022 apps due  Dec 2022-March 2023 | 2-3 Red Seal  ER/EE REP | In process |
| Floorcovering Installer | Red Seal Occupational Standards (RSOS) Development | July 29, 2022 apps due  Names to ESDC Sept 16/22  Work is Oct 17-Nov 4 | 2-3 Red Seal  ER/EE REP | Cancelled |
| Glazier | Peer Review – Red Seal Examination | July 11, 2022 apps due  ESDC Work Start July 15 | 2-3 Red Seal  ER/EE REP | Cancelled |
| Ironworker | Red Seal Occupational Standards (RSOS) Development | Work: Jan – Feb 2024 | 2-3 Red Seal  ER/EE REP | TBD |
| Painter and Decorator | Red Seal Examination Development  Red Seal Exam – Peer Review  Red Seal Exam - Translation | July 29, 2022 apps due  Names due: Oct 19/22  Work: Nov 21-25 in Ottawa  Work: Jan 2023-March 2024  Work: September 2023 | 2-3 Red Seal  ER/EE REP  1 Red Seal    2-3 Red Seal  ER/EE REP  1 Red Seal  Bilingual | In process  TBD  TBD |

Industry Working Group Applications:

<https://www.gov.mb.ca/wd/apprenticeship/boardpac/iwg.html>