REGULATORY AND TECHNICAL TRAINING WORK PLAN

2022/2023 FISCAL YEAR

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Trade Name** | **Task** | **Date Required** | **# IWG Members** | **Status** |
| Carpenter | Translation Workshop | Names due January 20, 2023Work: Mar 13-16/23 in OTT | 1 Red SealER/EE REPBilingual | Names Needed |
| Construction Craft Worker | Red Seal Occupational Standards (RSOS) Development | August 1, 2023 apps dueNames due Sept 16, 2023Work: Nov 6-24/23 | TBD | TBD |
| Crane – Mobile Crane Operator | * Red Seal Examination Development – MB lead
 | July 29, 2022 apps dueWork:* Part 1:Now-March 20, 23

2 yr commitment* Part 2: April –May 2023
 | * 3 Red Seal

ER/EE REP* 4 Red Seal

ER/EE REPDifferent members | Names Needed |
| * Translation Workshop
 | August 12, 2022 app dueName to ESDC is Sept 2Work: Dec 13-15 in Ottawa | 1 Red Seal BilingualDevelopment workshop held in Ottawa. | Complete |
| Crane – Tower Crane Operator | Red Seal Occupational Standards (RSOS) Development | July 29, 2022 apps dueDec 2022-March 2023 | 2-3 Red SealER/EE REP | In process |
| Floorcovering Installer | Red Seal Occupational Standards (RSOS) Development | July 29, 2022 apps dueNames to ESDC Sept 16/22Work is Oct 17-Nov 4 | 2-3 Red SealER/EE REP | Cancelled |
| Glazier | Peer Review – Red Seal Examination | July 11, 2022 apps dueESDC Work Start July 15 | 2-3 Red SealER/EE REP | Cancelled |
| Ironworker | Red Seal Occupational Standards (RSOS) Development | Work: Jan – Feb 2024 | 2-3 Red SealER/EE REP | TBD |
| Painter and Decorator | Red Seal Examination DevelopmentRed Seal Exam – Peer ReviewRed Seal Exam - Translation | July 29, 2022 apps dueNames due: Oct 19/22Work: Nov 21-25 in OttawaWork: Jan 2023-March 2024Work: September 2023 | 2-3 Red SealER/EE REP 1 Red Seal  2-3 Red SealER/EE REP 1 Red SealBilingual | In processTBDTBD |

Industry Working Group Applications:

<https://www.gov.mb.ca/wd/apprenticeship/boardpac/iwg.html>